Innovation Case Study
Title of innovation
Distraction Therapy Collection Tracking System
Please provide a very brief description of your innovation? / One or two sentences about the innovation.
The Distraction Therapy Collection is a range of specialist equipment, including touch screen monitors and tablet computers, which healthcare professionals can use at point of care to distract and stimulate patients with dementia. / In a successful collaboration with Older Adults Mental Health Team and the Dementia Support Team, Library and Knowledge Services created a unique online tracking system to manage the established collection. The repository for the collection is now managed by the Library.
During which period did you implement your innovation? / Please state which year (and month if possible).
February 2018
What was the driver for your innovation? / Please describe the issue or challenge that your innovation addresses / (100 words max)
The Library and Knowledge Services Manager was invited to the Trust Dementia Steering Group Meeting to present on how other NHS library services were developing reminiscence collections. These collections consisted of books or activities that hospital staff could loan to engage with service users. The committee explored how a similar service could be implemented at Walsall. / The Advanced Nurse Practitioner of the Older Adults Mental Health Team was at the meeting and confirmed that the Trust already had an established specialist collection of resources for patients with dementia called the Distraction Therapy Collection. However it was not being used to its full potential and there was no formal loan procedure.
What did you do? Please describe your aims and objectives and how you implemented these / (200 words max)
It was agreed the Library Manager and the Advanced Nurse Practitioner would work in partnership to review how to manage the collection more effectively and promote. The Library Manager setup a Task and Finish Group for the project and assigned the Evidence Based Information Specialist to lead. The Advanced Nurse Practitioner designated a Dementia Support Worker with knowledge of the equipment and its use on wards. The nominated staff arranged a series of meetings to undertake the agreed action plan. / The collection was moved from the Older Peoples Mental Health Team’s office to the library to alleviate storage problems. There wasn’t a record of what in the collection so an inventory was compiled, missing items replaced and checks made to ensure all equipment worked. The absence of a formal loaning procedure made it difficult to track equipment and make borrowers accountable for damaged or misplaced items so a loan procedure was devised and a website created explaining the process. Equipment was labelled and added to the library catalogue so it could be tracked. Furthermore, the library team received training on using the specialist equipment and My Life software. Ward visits were undertaken to explain the formalised loan process to Ward Managers and register their wards on the new system.
What methods were used to evaluate your innovation?
The library management system (Koha) was used to catalogue specialist equipment using a “Distraction Therapy Collection” series heading and library cards were issued to wards to loan items. Koha reports provide usage data to demonstrate that the service is being used and which items in the collection are loaned. This information informs promotional activities and collection development. / Once the loan procedure was devised, certain wards were identified where the process was piloted. This enabled the library team to gain direct feedback from the Ward Managers about the loan procedure and elements were streamlined before the process was formalised and extended to all wards. The loan procedure will be further reviewed in response to feedback. / The Library Manager attends the Dementia Steering Group Meeting and provides a progress report about the project. Feedback from the committee and the Advanced Nurse Practitioner informs project developments. / Implementation of the formalised loan procedure has enabled the service currently used to distract and stimulate patients with dementia, to be extended to engage patients with learning disabilities and vulnerable adults.
What were the outcomes and key learning points? / (200 words max)
The Distraction Therapy Collection project has been an excellent opportunity to work in partnership with clinical teams and make a real difference in supporting patient care. / The Library Manager was proactive in showcasing best practice of how libraries supported clinical teams and helped engage clinicians about the project. / The Evidence Based Information Specialist gained a clear understanding of the challenges the Dementia Support Worker experienced managing the collection and their collaborative approach facilitated identifying practical solutions to overcome them. / Training provided by the Dementia Support Worker on using the specialist equipment and My Life software enabled the library team to gain confidence passing this knowledge to borrowers. / The Dementia Support Worker’s knowledge of the wards and key contacts helped library staff implement the project. Visiting Ward Managers at their work base enabled loan procedures to be tailored to the demands of staff working on busy wards. Furthermore, it provides an excellent outreach opportunity. / An official launch of the new service at the Trust Dementia Conference was effective in raising awareness about the Distraction Therapy Collection. / The service has been effective in improving access to the Distraction Therapy Collection by supporting healthcare professionals make optimum use of specialist equipment to engage service users. Furthermore, it streamlined the loaning process by creating a formalised procedure.
Please provide a short quote from a member of staff who has benefitted from the innovation / Please include name and job title / (100 words max)
This has been a fantastic addition to our expanding services that we are able to provide for people with dementia in Walsall. It has given us a very structured approach to be able to catalogue, clean and loan out the equipment. Not only has this innovation been a huge bonus from a practical point of view with regard to the equipment loan point of view but the service now has such a professional approach to it all with regard to advertising, raising awareness, social media etc. The Library team in conjunction with Older Peoples Mental Health and Pathways for Life have been able to lift the profile of service provision to another level. I’m convinced that this is the beginning of really positive things to come for the future. / Debbie Shaw Advanced Nurse Practitioner Older Peoples Mental Health, Walsall Healthcare NHS Trust
Further information Please use this field to enter any relevant further information, such as links, references or associated innovations
Equipment Loan Services web page https://www.walsallhealthcare.nhs.uk/library/equipment-loan-service-1.aspx / Distraction Therapy Collection web page / https://www.walsallhealthcare.nhs.uk/library/distraction-therapy-collection.aspx
Your name and job title
Jacqui Watkeys, Library and Knowledge Services Manager / in HEE
Your Library & Knowledge Service & Organisation / Please provide the name of your service and organisation in which it is based
Library and Knowledge Services / Walsall Healthcare NHS Trust / Manor Hospital, Moat Road, Walsall, WS2 9PS.
Your email address
Jacqui.Watkeys@walsallhealthcare.nhs.uk
Your phone number
01922 656628