Resource Discovery Workstream: high level plan 2022-23
	April-June 2022	July-Sep 2022	Oct-Dec 2022	Jan-March 2023
Content
National contracts re-procurement planning1			Yes	Yes
Work to progress open access and repositories
NHS Knowledge and Library Hub
Ongoing enhancements to Hub search, discovery and linking	Yes	Yes	Yes	Yes
Ongoing development of the Hub Service Desk
North East and Midlands LMS catalogue integrations
East, KSS and London catalogue integrations
Review of new EBSCO EDS interface & decision about whether to use
Regional library management systems
East of England and Kent, Surrey & Sussex new systems go live
London and Midlands phased expansions
North East re-procurement planning
North West options engagement / procurement planning		Yes	Yes	Yes
South West re-procurement planning			Yes	Yes
Yorkshire and Humber (options engagement / procurement planning)		Yes	Yes	Yes
Inter-library sharing, document supply and websites
Review options to make it easier for library staff to source articles	Yes	Yes
Start to migrate regional KLS websites to national platform
Negotiate new CLA Licence2

Notes
1 – all current national contracts (databases, full text journals, clinical decision support tool, OUP and Wiley books) run to end March 2024
2 – the current CLA Licence for the NHS in England runs to end March 2023