Regional LMS Roadmap 2023-24
Overarching KPI: 75% of NHS Knowledge and Library Services participating in regional LMSs by March 2024
1 service joining KSS
Yorkshire and Humber phase 1 completes
Koha bookings module deployed in North West
2 services joining North East
2 services joining London
Sep
Dec
Apr
Jun
2024
2023
Koha ILL module developments . Improvements to Axiell ILDS functionality in the South West
Creation of core collection of commonly used reports
Common e-book cataloguing procedures and standards
Standard catalogue integration with the NHS Knowledge Hub
East of England/KSS involved in testing/review of ILL module developments and core reports
Adoption of HEE Service Desk by all regions
North West phases 2 and 3 complete
North West phase 1 completes
Task and finish group to develop good practice guidelines for stock retention

---
Regional LMS Roadmap 2024-26
Overarching KPI: 90% of NHS-provided Knowledge and Library Services participating in regional LMSs by March 2025
Phase 1 Koha ILL module developments deployed
YorCat phase 4 complete
SWIMS Axiell reprocurement
NoW phase 5
complete
PrintDOCs launches
Apr
Dec
Sep
Jun
Apr
2024
2025
Start of reprocurement of all regional LMSs
YorCat phase 3b completes
NoW phase 6 complete
Collections management guidance published
Aspen Pilot
Koha ILL module developments. Improvements to Axiell ILDS functionality in the South West.
Collaborative work to harmonise LMS policies and practices
Enhancements to e-book access in Hub/LMS integrations
Standardise catalogue integration with the NHS Knowledge Hub
Enhancements to document supply and inter-lending infrastructure.